## Type-cure
|  | Where found | [5 empty] | Who failed |  |  |  | Damage | [5 empty] | Cure type
| Damage Causes in Government IT projects 26-12-2019 | Land Registry | Travel card | Police case mgmt. | Debt collection | Healh record | Others | Customer | Consultant | Supplier | Government | Time | Cost | Business results | User satisfaction | Supplier loss | Feasibility doubts | Familiar - ignored | Unfamiliar | Misinformed | Cure unknown | Søren Lauesen slauesen@itu.dk Full report: www.itu.dk/people/slauesen/ SorenDamages.html
| Number of observations: | 18 | 13 | 18 | 17 | 15 | 11 | 32 | 16 | 13 | 5 | 26 | 26 | 24 | 18 | 16 | 9 | 23 | 17 | 3 | 5
ID | Analysis | [20 empty] | Cure
A1 | Doesn't identify user needs and win-win | x | x | x | x | x | Virk.dk | x | x |  |  | x | x | x | x | x | x | x |  |  |  | Study as-is and plan to-be
A2 | Requirements don't cover customer needs | x | x | x | x | (x) |  | x | x |  |  | x | x | x | x | x |  |  | x |  |  | Problem oriented requirements (SL-07)
A3 | Describes the solution in detail. No freedom to the supplier |  |  | x | x | (x) | DMR | x | x |  |  | x | x |  |  | x |  |  | x |  |  | SL-07
A4 | Makes heavy demands and believes it is for free | x | (x) |  |  | (x) | Pens | x | x |  |  | x | x | [5 empty] | x |  |  | Scope management, Open target requirements (part of SL-07)
A5 | Oversells technology, e.g. SOA, web-based, workflow engine | x |  | x | X |  |  |  | x |  | x | x | x |  |  | x | x |  | x | x |  | Check technology (get second opinion & ask technology users), Ask expert developers
A6 | Multi-vendor strategy - makes us supplier independent ! ? |  |  |  | x |  | H:S Munic. | x |  |  | x | x | x | [5 empty] | x | x |  | Third-party can integrate & exit strategy, Central database & flex SOA
A7 | Wants everything at once, e.g. cover the entire country or all types of debt | x |  | x | x | X |  | x |  |  |  | x | x | x | x |  |  | x |  |  |  | Pilot test, Deploy part-by-part
A8+F | Doesn't plan the new work processes |  | x | x |  | x |  | x |  |  |  | x | x | x | x | x |  | x | x |  |  | Plan to-be, SL-07 reqs (B1 and C)
A9 | No feasible solution. Data missing, performance dubious, etc. |  |  | x | x |  |  | x |  |  |  |  | x | x |  | x | x | x |  |  |  | Ask experts, Early proof of concept (POC)
A10 | Surprising rule complexity. |  | (x) |  | x | x |  | x |  |  | x | x | x | x | x |  |  | x |  |  |  | Deploy part-by-part, Expert spec of complex cases
Acquisition
B1 | Supplier too optimistic - you must lie to win |  | x |  |  |  | H:S |  |  | x |  | x | x |  |  | x |  | x |  |  |  | POC
B2 | Wrong selection criteria |  | x |  |  | x | ESDH | x | x |  |  | x | x | x | x |  |  |  | x |  | x | SL-07 (B4-6)
B3 | Wrong cost estimates |  | x | x | x |  |  | x | x |  |  | x | x |  |  | x |  | x | x |  |  | Function points (based on SL-07 reqs), Cost checklist
Design
C1 | Doesn't ensure usability, even when they know how | x |  |  |  | x |  | x | x | x |  |  |  | x | x |  |  | x |  |  |  | Early prototypes & usability tests
C2 | Designs user screens too late | x | x | [5 empty] | x | x |  | x | x | x | x | x |  | x |  |  |  | Early prototypes & usability tests
C3 | Accepts the solution description without understanding it |  | x |  |  |  |  | x |  | x |  | x | x |  |  | x |  | x |  |  |  | Early prototypes & usability tests
C4 | Cannot see how far the supplier is | x | x |  |  |  |  | x | x | x |  | x | x |  |  | x |  | x | x |  |  | Early prototypes, Scope mgmt, Monitor remaining work hours, Ask expert developers
C5+A | My way without considering the supplier's way |  |  | x |  |  |  | x |  |  |  | x | x | [5 empty] | x |  |  | SL-07 reqs
Programming
D1 | Supplier accepts the expensive requirements interpretation |  | x | x | [5 empty] | x | [5 empty] | x |  | x | x |  |  | Replan, SL-07 reqs
D2 | Surprises with system integration | x |  | x | x | x |  | x | x | x |  | x | x | x | x |  | x | x |  |  |  | POC, Pilot test
Test
E1 | Deploys the system with insufficient testing | x |  |  | x | x |  | x |  | x |  |  |  | x | x |  |  | x |  |  |  | Pilot test, Ask expert developers
Deployment
F1 | Deploys the system with insufficient support or training | x |  | x |  | x |  | x | x |  |  |  |  | x | x |  | x | x |  |  |  | Plan new work, Usability tests, Pilot test, Deploy part-by-part
F2 | The system is not used as intended |  |  | x | x | x |  | x | [5 empty] | x |  |  | x |  | x |  |  | Observe at pilot test, Follow-up study
F3+A | Wrong estimate of human performance | x |  |  |  | x |  | x | [5 empty] | x | x |  |  |  | x |  |  | Check at POC, Check at pilot test
Management
G1 | No business goals - or forgets them on the way |  | (x) | x | x | x |  | x |  |  |  | x | x | x |  |  |  | x |  |  |  | Monitor business case regularly
G2 | Doesn't reschedule, but assumes the rest can be compressed | x |  |  |  | x |  | x | x |  |  |  |  | x | x |  |  | x |  |  |  | Replan at surprises
G3 | The project grows without anybody noticing |  |  | x |  |  |  | x |  | x |  | x | x |  |  | x | x |  | x |  |  | Scope mgmt, Monitor remaining work hours
G4 | Doesn't face the danger. Risk assessment downplays the danger | x | x |  | x |  |  | x | x | x |  | x | x | x | x | x |  | x |  |  |  | Correct risk management, plan what-if
G5 | The financial incentive disappears and parties fight instead of cooperate |  | x | x |  |  | Pens | x |  | x |  | x | x |  | x | x |  | x | x |  |  | Monitor remaining work hours, Scope mgmt, Replan (SL-07 K2), Contract payment plan
G6 | Cashes the benefit before it is harvested, e.g. sacks too early | x |  |  | x | x |  | x |  |  | x |  |  | x |  |  |  | x |  |  | x | Replan at surprises + ?
G7 | Lack of management involvement |  |  | x | x |  |  | x |  |  |  | x | x | x |  |  | x |  | x |  |  | Give mgmt IT-insight, SL-07 contract 3.4
G8 | Excessive management or expert involvement | x | [5 empty] | x | x |  |  |  |  | x | x | [5 empty] | x | ?
G9 | Too large committees/work groups without competencies |  | x |  |  | x |  | x |  |  |  | x | x | x | x | x |  | x |  |  |  | Small task force with authority, SL-07 contract 3.4
G10 | Excessive user involvement |  |  | (x) |  | (x) |  | x | x |  |  | x | x | x |  |  |  | x |  | x |  | Small task force with authority
G11+B | Believes law blocks sound approaches, e.g. talking to suppliers or pilot test | x |  |  | X |  | H:S book. | x |  |  | x |  |  | x | x |  |  |  | x |  | x | Use constructive lawyers and make them part of the team + ?
G12 | Insufficient staffing | x |  |  |  |  | Pens |  |  | x |  | x |  | x |  |  |  | x |  |  |  | Monitor remaining work hours, SL-07 contract 2.3 and 3.4
G13 | Doesn't find the root cause |  |  | x |  |  | Denver | x |  | x |  | x | x |  |  |  | x |  |  |  | x | Ask expert developers, Give mgmt IT-insight

## Cures
Cures
| Damage cures Søren Lauesen 21-12-2019 slauesen@itu.dk | CA1 Problem-oriented reqmts (SL-07) | CE1 Pilot test / deployment test | CA3 Scope mgmt & function points | CC1 Early prototypes & test | CG7 Ask expert developers | CA8 Early proof-of-concept (POC) | CC2 Monitor remaining work | CG1 Replan | CA2 Study as is, plan to-be | CF1 Deploy part-by-part | CG2 Small task force with authority | CG8 Problem-oriented contract (SL-07) | CA4 Expert involvement | CG6 Give mgmt IT-insight | CA5 Check technology | CA6 Central database & flex SOA | CA7 Third-party integrate & exit | CB1 Cost checklist | CF2 Follow-up study | CG3 Monitor business case | CG4 Correct risk management | CG5 Constructive lawyers | Cure (partially) unknown | Total
ID | Analysis | 9 | 6 | 5 | 5 | 5 | 4 | 4 | 4 | 3 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4 | 70
A1 | Doesn't identify user needs and win-win | x | [7 empty] | x | [14 empty] | 2
A2 | Requirements don't cover customer needs | x | [22 empty] | 1
A3 | Describes the solution in detail. No freedom to the supplier | x | [22 empty] | 1
A4 | Makes heavy demands and believes it is for free | x |  | x | [7 empty] | x | [12 empty] | 3
A5 | Oversells technology, e.g. SOA, web-based |  |  |  |  | x | [9 empty] | x | [8 empty] | 2
A6 | Multi-vendor strategy -supplier independent ! ? | [15 empty] | x | x | [6 empty] | 2
A7 | Wants everything at once, e.g. cover the entire country or all types of debt |  | x | [7 empty] | x | [13 empty] | 2
A8+F | Doesn't plan the new work processes | x | [7 empty] | x | [14 empty] | 2
A9 | No feasible solution. Data missing, performance dubious, etc. |  |  |  |  | x | x | [6 empty] | x | [10 empty] | 3
A10 | Surprising rule complexity. | [9 empty] | x |  |  | x | [10 empty] | 2
Acquisition
B1 | Supplier too optimistic - you must lie to win | [5 empty] | x | [17 empty] | 1
B2 | Wrong selection criteria | x | [22 empty] | 1
B3 | Wrong cost estimates | x |  | x | [14 empty] | x | [5 empty] | 3
Design
C1 | Doesn't ensure usability, even when they know how |  |  |  | x | [19 empty] | 1
C2 | Designs user screens too late |  |  |  | x | [19 empty] | 1
C3 | Accepts solution description without understanding it |  |  |  | x | [19 empty] | 1
C4+D | Cannot see how far the supplier is |  |  | x | x | x |  | x | [16 empty] | 4
C5+A | My way without considering the supplier's way | x | [22 empty] | 1
Programming
D1 | Supplier accepts the expensive requirements interpretation | x | [6 empty] | x | [15 empty] | 2
D2 | Surprises with system integration |  | x |  |  |  | x | [16 empty] | x | 2
Test
E1 | Deploys the system with insufficient testing |  | x |  |  | x | [18 empty] | 2
Deployment
F1 | Deploys with insufficient support or training |  | x |  | x |  |  |  |  | x | x | [13 empty] | 4
F2 | The system is not used as intended |  | x | [16 empty] | x |  |  |  |  | 2
F3+A | Wrong estimate of human performance |  | x |  |  |  | x | [17 empty] | 2
Management
G1 | No business goals - or forgets them on the way | [19 empty] | x |  |  |  | 1
G2 | Doesn't reschedule, but assumes the rest can be compressed | [7 empty] | x | [15 empty] | 1
G3 | The project grows without anybody noticing |  |  | x |  |  |  | x | [16 empty] | 2
G4 | Doesn't face the danger. Risk assessment downplays the danger | [20 empty] | x |  |  | 1
G5 | The financial incentive disappears and parties fight instead of cooperate |  |  | x |  |  |  | x | x |  |  |  | x | [11 empty] | 4
G6 | Cashes the benefit before it is harvested, e.g. sacks too early | [7 empty] | x | [14 empty] | x | 1
G7 | Lack of management involvement | [11 empty] | x |  | x | [9 empty] | 2
G8 | Excessive management or expert involvement | [22 empty] | x | 0
G9 | Too large committees/work groups without competencies | [10 empty] | x | [12 empty] | 1
G10 | Excessive user involvement | [10 empty] | x | [12 empty] | 1
G11+B | Believes law blocks sound approaches, e.g. talking to suppliers or pilot test | [21 empty] | x | x | 0
G12 | Insufficient staffing | [6 empty] | x |  |  |  |  | x | [11 empty] | 2
G13 | Doesn't find the root cause |  |  |  |  | x | [8 empty] | x | [9 empty] | 2

## VisibleDamage1
|  | Land Registry |  |  |  | Travel Card |  |  |  |  | Police Case Management |  |  |  |  | Debt Collection
| Visible Damages 22-12-2019 | Development time 1.2 to 2.7 years | Lost savings+ scans: +160 M DKK | 50 days handling. Should be 10 | Hard to use | Development time 3.5 to 7.5 years | Internal costs from 30 to 100 M DKK | Little benefit to transport operators | Initially low user satisfaction | Supplier loss 500+ M DKK | Development time 3.7 to 7 years | SW cost 173 to 354 M DKK | Negative business case: Project closed | Supplier lost 50+ M DKK | Feasibility doubts | Development time 2.5 to 8.5 years | SW cost 144 to 600 M DKK | Benefit lost. Collection delayed for years | Feasibility doubts, project cut down
| Number of observations: | 7 | 6 | 12 | 9 | 11 | 11 | 1 | 2 | 12 | 10 | 9 | 7 | 6 | 8 | 12 | 12 | 13 | 4
ID | Analysis
A1 | Doesn't identify user needs and win-win |  |  | x | x | x | x |  |  | x | x | x | x | x | x | x | x | x
A2 | Requirements don't cover customer needs | x | x | x | x | x | x |  | x | x | x | x | x |  |  | x | x | x
A3 | Describes the solution in detail. No freedom to the supplier | [9 empty] | x | x |  | x |  |  |  | x
A4 | Makes heavy demands and believes it is for free | x | x
A5 | Oversells technology, e.g. SOA, web-based, workflow engine | x | x | [7 empty] | x | x |  | x | x | x | x |  | x
A6 | Multi-vendor strategy - makes us supplier independent ! ? | [14 empty] | x | x |  | x
A7 | Wants everything at once, e.g. cover the entire country or all types of debt |  |  | x | x | [5 empty] | x | x | x |  |  | x | x | x
A8 | Doesn't plan the new work processes |  |  |  |  | x | x |  | x | x | x | x | x
A9 | No feasible solution. Data missing, performance dubious, etc. | [13 empty] | x | x | x | x
A10 | Surprising rule complexity. | [14 empty] | x | x | x | x
Acquisition
B1 | Supplier too optimistic - you must lie to win |  |  |  |  | x | x |  |  | x
B2 | Wrong selection criteria |  |  |  |  | x | x |  |  | x |  | x | x
B3 | Wrong cost estimates | [9 empty] | x |  |  | x |  | x | x
Design
C1 | Doesn't ensure usability, even when they know how |  |  | x | x
C2 | Designs user screens too late | x | x | x | x | x | x |  |  | x
C3 | Accepts the solution description without understanding it |  |  |  |  | x | x |  |  | x
C4 | Cannot see how far the supplier is | x |  |  |  | x | x |  |  | x
C5 | My way without considering the supplier's way | [9 empty] | x | x
Programming
D1 | Supplier accepts the expensive requirements interpretation | [8 empty] | x |  |  |  | x
D2 | Surprises with system integration | x | x | [12 empty] | x | x | x
Test
E1 | Deploys the system with insufficient testing | [16 empty] | x
Deployment
F1 | Deploys the system with insufficient support. or training |  |  | x | x | [9 empty] | x
F2 | The system is not used as intended. | [13 empty] | x |  |  | x
F3 | Wrong estimate of human performance |  |  | x
Management
G1 | No business goals - or forgets them on the way | [6 empty] | x |  |  |  |  | x |  |  | x | x | x
G2 | Doesn't reschedule, but assumes the rest can be compressed |  |  | x
G3 | The project grows without anybody noticing | [9 empty] | x | x |  | x | x
G4 | Doesn't face the danger. The risk assessment downplays the danger | x | x | x | x | x | x |  |  | x | [5 empty] | x | x | x | x
G5 | The financial incentive disappears and parties fight instead of cooperate |  |  |  |  | x | x |  |  | x | x |  |  |  | x
G6 | Cashes the benefit before it is harvested, e.g. sacks too early |  |  | x | [13 empty] | x
G7 | Lack of management involvement | [11 empty] | x |  | x | x | x | x
G8 | Excessive management or expert involvement |  |  | x | x
G9 | Too large steering committees/work groups without competencies |  |  |  |  | x | x |  |  | x
G10 | Excessive user involvement | [9 empty] | (x)
G11+B | Believes law blocks sound approaches, e.g. talking to suppliers or pilot test |  |  | x | x
G12 | Insufficient staffing | x |  | x
G13 | Doesn't find the root cause |  |  |  |  | x | x

## VisibleDamage2
Health Record
| Visible Damages 21-12-2019 | Time - no damage | Cost - no damage | Operating costs - no damage | Initially low productivity | Quality: No changes yet | User satisfaction initially low
| Number of observations: | 0 | 0 | 0 | 15 | 9 | 14
ID | Analysis
A1 | Doesn't identify user needs and win-win |  |  |  | x | x | x
A2 | Requirements don't cover customer needs |  |  |  | (x)
A3 | Describes the solution in detail. No freedom to the supplier |  |  |  | (x)
A4 | Makes heavy demands and believes it is for free
A5 | Oversells technology, e.g. SOA, web-based, workflow engine
A6 | Multi-vendor strategy - makes us supplier independent ! ?
A7 | Wants everything at once, e.g. cover the entire country or all types of debt |  |  |  | X | x | X
A8 | Doesn't plan the new work processes |  |  |  | X | X | X
A9 | No feasible solution. Data missing, performance dubious, etc.
A10 | Surprising rule complexity. |  |  |  | x |  | x
Acquisition
B1 | Supplier too optimistic - you must lie to win
B2 | Wrong selection criteria |  |  |  | x | x | x
B3 | Wrong cost estimates
Design
C1 | Doesn't ensure usability, even when they know how |  |  |  | x |  | x
C2 | Designs user screens too late
C3 | Accepts the solution description without understanding it
C4 | Cannot see how far the supplier is
C5 | My way without considering the supplier's way
Programming
D1 | Supplier accepts the expensive requirements interpretation
D2 | Surprises with system integration |  |  |  | x |  | x
Test
E1 | Deploys the system with insufficient testing |  |  |  | x | x | x
Deployment
F1 | Deploys the system with insufficient support. or training |  |  |  | x | x | x
F2 | The system is not used as intended. |  |  |  | x | x | x
F3 | Wrong estimate of human performance |  |  |  | X |  | x
Management
G1 | No business goals - or forgets them on the way |  |  |  | x
G2 | Doesn't reschedule, but assumes the rest can be compressed |  |  |  | x | x | x
G3 | The project grows without anybody noticing
G4 | Doesn't face the danger. The risk assessment downplays the danger
G5 | The financial incentive disappears and parties fight instead of cooperate
G6 | Cashes the benefit before it is harvested, e.g. sacks too early |  |  |  | x |  | x
G7 | Lack of management involvement
G8 | Excessive management or expert involvement
G9 | Too large steering committees/work groups without competencies |  |  |  | x | x | x
G10 | Excessive user involvement |  |  |  | (x)
G11+B | Believes law blocks sound approaches, e.g. talking to suppliers or pilot test
G12 | Insufficient staffing
G13 | Doesn't find the root cause